## Project schedule
| HAPAG BAYANIHAN: A community Kitchen and Food Assistance Management System | [5 empty] | Project start: | [7 empty] | 2025-08-29
| Joe Lito Vince Corminal | Carlo Gelicame |  |  |  |  | Display week: | [7 empty] | 1
[7 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [13 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-08-25 to 2025-12-26
 | time axis 2025-08-25 to 2025-12-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
WEEKLY MILESTONE 1: The Final output of your daily Task
| Brainstorming Thesis Title | Carlo Gelicame | 100% | 2025-08-11 | 2025-08-15 | 5
| Approval of Thesis Title | Carlo Gelicame & Joe Lito Vince Corminal | 100% | 2025-08-12 | 2025-08-18 | 7
| Finding Thesis Adviser | Joe Lito Vince Corminal | 100% | 2025-08-13 | 2025-08-18 | 6
WEEKLY MILESTONE 2: Stakeholder Analysis & Requirements Gathering
| Identify stakeholder groups | Carlo Gelicame | 100% | 2025-08-18 | 2025-08-25 | 8
| Conduct interviews / surveys / focus groups | Joe Lito Vince Corminal | 100% | 2025-08-18 | 2025-08-25
| Document stakeholder needs & expectations. | Carlo Gelicame | 0% | 2025-08-18 | 2025-09-02
| Create requirement checklist | Joe Lito Vince Corminal | 0% | 2025-08-18 | 2025-09-02
WEEKLY MILESTONE 3: Backend & Database Development
| Set up database server/environment | Joe Lito Vince Corminal | 90% | 2025-08-26 | 2025-09-20 | 26
| Design database schema | Carlo Gelicame | 100% | 2025-08-26 | 2025-09-10
| Test CRUD operations | Joe Lito Vince Corminal | 0% | 2025-08-26 | 2025-09-10 | 16
WEEKLY MILESTONE 4:System Architecture Design
| Design Data Flow | Carlo Gelicame | 0% | 2025-09-01 | 2025-09-21 | 21
| Define System Components | Joe Lito Vince Corminal | 0% | 2025-09-01 | 2025-09-21 | 21
| Create System Architecture Diagram | Carlo Gelicame | 0% | 2025-09-01 | 2025-09-21
| Review Architecture | Joe Lito Vince Corminal | 0% | 2025-09-01 | 2025-09-21
WEEKLY MILESTONE 5:Use Case & User Story Development
| Draw Use Case Diagram | Joe Lito Vince Corminal | 0% | 2025-09-10 | 2025-09-25
| Define Actors and System Boundaries | Carlo Gelicame | 0% | 2025-09-10 | 2025-09-25
| Review & Validate Use Cases | Joe Lito Vince Corminal | 0% | 2025-09-10 | 2025-09-25
WEEKLY MILESTONE 6:UI/UX Design using Figma
| Identify functionality of each button | Carlo Gelicame | 0% | 2025-09-18 | 2025-10-03 | 16
| Create UI design | Joe Lito Vince Corminal | 0% | 2025-09-18 | 2025-10-18 | 31
| Apply Button Functionality in UI Design | Carlo Gelicame | 0% | 2025-09-18 | 2025-10-18
WEEKLY MILESTONE 7:Frontend Development (Web & Mobile)
| Set up frontend frameworks | Joe Lito Vince Corminal | 0% | 2025-09-26 | 2025-10-26 | 31
| Implement authentication pages | Carlo Gelicame | 0% | 2025-09-26 | 2025-10-27 | 32
| Build user dashboards (role-based) | Joe Lito Vince Corminal | 0% | 2025-09-26 | 2025-10-28
| Design core UI components | Carlo Gelicame | 0% | 2025-09-26 | 2025-10-28
| Integrate backend APIs | Joe Lito Vince Corminal | 0% | 2025-09-26 | 2025-10-29
| Implement responsive design | Carlo Gelicame | 0% | 2025-09-26 | 2025-10-30
| Apply UI/UX standards | Joe Lito Vince Corminal | 0% | 2025-09-26 | 2025-10-31
| Deploy frontend apps | Carlo Gelicame | 0% | 2025-09-26 | 2025-11-01
WEEKLY MILESTONE 8: Integration of ML-based Features
| Train ML Models (Prototype Stage) | Joe Lito Vince Corminal | 0% | 2025-10-16 | 2025-11-15 | 31
| Convert to Lightweight Models | Carlo Gelicame | 0% | 2025-10-16 | 2025-11-16 | 32
| Backend Integration | Joe Lito Vince Corminal | 0% | 2025-10-16 | 2025-11-17
| Frontend Integration (Web and Mobile) | Carlo Gelicame | 0% | 2025-10-16 | 2025-11-18
WEEKLY MILESTONE 9:Pilot Deployment in Community
| Prepare Deployment Environment | Joe Lito Vince Corminal | 0% | 2025-11-18 | 2025-11-30 | 13
| Select Pilot Community | Carlo Gelicame | 0% | 2025-11-18 | 2025-11-30 | 13
| Launch Pilot Testing | Joe Lito Vince Corminal | 0% | 2025-11-18 | 2025-11-30
| Monitor System Performance | Carlo Gelicame | 0% | 2025-11-18 | 2025-11-30
| Gather Community Feedback | Joe Lito Vince Corminal | 0% | 2025-11-18 | 2025-11-30
| Analyze Pilot Results | Carlo Gelicame | 0% | 2025-11-18 | 2025-11-30
| Launch Pilot Testing | Joe Lito Vince Corminal | 0% | 2025-11-18 | 2025-11-30
WEEKLY MILESTONE 10:Final Thesis Manuscript Preparation
| Organize Thesis Structure (Chapters | Joe Lito Vince Corminal & Carlo Gelicame | 0% | 2025-12-01 | 2025-12-12 | 12
| Write and Refine Content | Joe Lito Vince Corminal & Carlo Gelicame | 0% | 2025-12-01 | 2025-12-12 | 12
| Formatting & Styling | Joe Lito Vince Corminal & Carlo Gelicame | 0% | 2025-12-01 | 2025-12-12
| Proofreading & Review | Joe Lito Vince Corminal & Carlo Gelicame | 0% | 2025-12-01 | 2025-12-12
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.